## Timeline
Start Date | Hours of per week | Estimated Date of Completion
Enter the date you started studying | Enter the number you will commit | Lower Bound | Upper Bound
2023-01-02 | 20 | 2024-09-21 14:24 | 2024-12-29 07:12

## Curriculum Data
Courses | Topic | Duration | Effort | Total Hours Lower Bound | Start Date | End Date Estimate Lower Bound | Total Hours Upper Bound | Start Date | End Date Estimate Upper Bound | Actual End Date | Prerequisites
Python for Everybody | Intro CS | 10 weeks | 10 hours/week | 100 | 2023-01-02 | 2023-02-06 | 100 |  |  |  | -
Introduction to Computer Science and Programming using Python | Intro CS | 9 weeks | 15 hours/week | 135 | 2023-02-06 | 2023-03-25 06:00 | 135 |  |  |  | high school algebra
How to Code - Simple Data | Core Programming | 7 weeks | 8-10 hours/week | 56 | 2023-03-25 06:00 | 2023-04-13 20:24 | 70 | 2023-01-02 | 2023-01-26 12:00 |  | -
How to Code - Complex Data | Core Programming | 6 weeks | 8-10 hours/week | 48 | 2023-04-13 20:24 | 2023-04-30 15:36 | 60 | 2023-01-26 12:00 | 2023-02-16 12:00 |  | How to Code: Simple Data
Programming Languages, Part A | Core Programming | 5 weeks | 4-8 hours/week | 20 | 2023-04-30 15:36 | 2023-05-07 15:36 | 40 | 2023-02-16 12:00 | 2023-03-02 12:00 |  | How to Code (Hear instructor)
Programming Languages, Part B | Core Programming | 3 weeks | 4-8 hours/week | 12 | 2023-05-07 15:36 | 2023-05-11 20:24 | 24 | 2023-03-02 12:00 | 2023-03-10 21:36 |  | Programming Languages, Part A
Programming Languages, Part C | Core Programming | 3 weeks | 4-8 hours/week | 12 | 2023-05-11 20:24 | 2023-05-16 01:12 | 24 | 2023-03-10 21:36 | 2023-03-19 07:12 |  | Programming Languages, Part B
Object-Oriented Design | Core Programming | 4 weeks | 4 hours/week | 16 | 2023-05-16 01:12 | 2023-05-21 15:36 | 16 | 2023-03-19 07:12 | 2023-03-24 21:36 |  | Basic Java
Design Patterns | Core Programming | 4 weeks | 4 hours/week | 16 | 2023-05-21 15:36 | 2023-05-27 06:00 | 16 | 2023-03-24 21:36 | 2023-03-30 12:00 |  | Object-Oriented Design
Software Architecture | Core Programming | 4 weeks | 2-5 hours/week | 8 | 2023-05-27 06:00 | 2023-05-30 01:12 | 20 | 2023-03-30 12:00 | 2023-04-06 12:00 |  | Design Patterns
Calculus 1A: Differentiation | Core Math | 13 weeks | 6-10 hours/week | 78 | 2023-05-30 01:12 | 2023-06-26 08:24 | 130 | 2023-04-06 12:00 | 2023-05-22 |  | high school math
Calculus 1B: Integration | Core Math | 13 weeks | 5-10 hours/week | 65 | 2023-06-26 08:24 | 2023-07-19 02:24 | 130 | 2023-05-22 | 2023-07-06 12:00 |  | Calculus 1A
Calculus 1C: Coordinate Systems & Infinite Series | Core Math | 6 weeks | 5-10 hours/week | 30 | 2023-07-19 02:24 | 2023-07-29 14:24 | 60 | 2023-07-06 12:00 | 2023-07-27 12:00 |  | Calculus 1B
Mathematics for Computer Science | Core Math | 13 weeks | 5 hours/week | 65 | 2023-07-29 14:24 | 2023-08-21 08:24 | 65 | 2023-07-27 12:00 | 2023-08-19 06:00 |  | Calculus 1C
The Missing Semester of Your CS Education | CS Tools | 2 weeks | 12 hours/week | 24 | 2023-08-21 08:24 | 2023-08-29 18:00 | 24 | 2023-08-19 06:00 | 2023-08-27 15:36 |  | -
Build a Modern Computer from First Principles: From Nand to Tetris | Core Systems | 6 weeks | 7-13 hours/week | 42 | 2023-08-29 18:00 | 2023-09-13 10:48 | 78 | 2023-08-27 15:36 | 2023-09-23 22:48 |  | C-like programming language
Build a Modern Computer from First Principles: Nand to Tetris Part II | Core Systems | 6 weeks | 12-18 hours/week | 72 | 2023-09-13 10:48 | 2023-10-08 15:36 | 108 | 2023-09-23 22:48 | 2023-10-31 18:00 |  | one of these programming languages, From Nand to Tetris Part I
Operating Systems: Three Easy Pieces | Core Systems | 10-12 weeks | 6 hours/week | 60 | 2023-10-08 15:36 | 2023-10-29 15:36 | 72 | 2023-10-31 18:00 | 2023-11-25 22:48 |  | algorithms, familiarity with C is useful
Computer Networking: a Top-Down Approach | Core Systems | 8 weeks | 4-12 hours/week | 32 | 2023-10-29 15:36 | 2023-11-09 20:24 | 96 | 2023-11-25 22:48 | 2023-12-29 13:12 |  | algebra, probability, basic CS
Divide and Conquer, Sorting and Searching, and Randomized Algorithms | Core Theory | 4 weeks | 4-8 hours/week | 16 | 2023-11-09 20:24 | 2023-11-15 10:48 | 32 | 2023-12-29 13:12 | 2024-01-09 18:00 |  | any programming language, Mathematics for Computer Science
Graph Search, Shortest Paths, and Data Structures | Core Theory | 4 weeks | 4-8 hours/week | 16 | 2023-11-15 10:48 | 2023-11-21 01:12 | 32 | 2024-01-09 18:00 | 2024-01-20 22:48 |  | Divide and Conquer, Sorting and Searching, and Randomized Algorithms
Greedy Algorithms, Minimum Spanning Trees, and Dynamic Programming | Core Theory | 4 weeks | 4-8 hours/week | 16 | 2023-11-21 01:12 | 2023-11-26 15:36 | 32 | 2024-01-20 22:48 | 2024-02-01 03:36 |  | Graph Search, Shortest Paths, and Data Structures
Shortest Paths Revisited, NP-Complete Problems and What To Do About Them | Core Theory | 4 weeks | 4-8 hours/week | 16 | 2023-11-26 15:36 | 2023-12-02 06:00 | 32 | 2024-02-01 03:36 | 2024-02-12 08:24 |  | Greedy Algorithms, Minimum Spanning Trees, and Dynamic Programming
Cybersecurity Fundamentals | Core Security | 8 weeks | 10-12 hours/week | 80 | 2023-12-02 06:00 | 2023-12-30 06:00 | 96 | 2024-02-12 08:24 | 2024-03-16 22:48 |  | -
Principles of Secure Coding | Core Security | 4 weeks | 4 hours/week | 16 | 2023-12-30 06:00 | 2024-01-04 20:24 | 16 | 2024-03-16 22:48 | 2024-03-22 13:12 |  | -
Identifying Security Vulnerabilities | Core Security | 4 weeks | 4 hours/week | 16 | 2024-01-04 20:24 | 2024-01-10 10:48 | 16 | 2024-03-22 13:12 | 2024-03-28 03:36 |  | -
Identifying Security Vulnerabilities in C/C++ Programming or Exploiting and Securing Vulnerabilities in Java Applications | Core Security | 4 weeks | 5 hours/week | 20 | 2024-01-10 10:48 | 2024-01-17 10:48 | 20 | 2024-03-28 03:36 | 2024-04-04 03:36 |  | -
Databases: Modeling and Theory | Core Applications | 2 weeks | 10 hours/week | 20 | 2024-01-24 10:48 | 2024-01-31 10:48 | 20 | 2024-04-11 03:36 | 2024-04-18 03:36 |  | core programming
Databases: Relational Databases and SQL | Core Applications | 2 weeks | 10 hours/week | 20 | 2024-01-17 10:48 | 2024-01-24 10:48 | 20 | 2024-04-04 03:36 | 2024-04-11 03:36 |  | core programming
Databases: Semistructured Data | Core Applications | 2 weeks | 10 hours/week | 20 | 2024-01-31 10:48 | 2024-02-07 10:48 | 20 | 2024-04-18 03:36 | 2024-04-25 03:36 |  | core programming
Machine Learning | Core Applications | 11 weeks | 4-6 hours/week | 44 | 2024-02-07 10:48 | 2024-02-22 20:24 | 66 | 2024-04-25 03:36 | 2024-05-18 06:00 |  | linear algebra
Computer Graphics | Core Applications | 6 weeks | 12 hours/week | 72 | 2024-02-22 20:24 | 2024-03-19 01:12 | 72 | 2024-05-18 06:00 | 2024-06-12 10:48 |  | C++ or Java, linear algebra
Software Engineering: Introduction | Core Applications | 6 weeks | 8-10 hours/week | 48 | 2024-03-19 01:12 | 2024-04-04 20:24 | 60 | 2024-06-12 10:48 | 2024-07-03 10:48 |  | Core Programming, and a sizable project
Ethics, Technology and Engineering | Core Ethics | 9 weeks | 2 hours/week | 18 | 2024-04-04 20:24 | 2024-04-11 03:36 | 18 | 2024-07-03 10:48 | 2024-07-09 18:00 |  | -
Intellectual Property Law in Digital Age | Core Ethics | 4 weeks | 2 hours/week | 8 | 2024-04-11 03:36 | 2024-04-13 22:48 | 8 | 2024-07-09 18:00 | 2024-07-12 13:12 |  | -
Data Privacy Fundamentals | Core Ethics | 3 weeks | 3 hours/week | 9 | 2024-04-13 22:48 | 2024-04-17 02:24 | 9 | 2024-07-12 13:12 | 2024-07-15 16:48 |  | -
Parallel Programming | Advanced Programming | 4 weeks | 6-8 hours/week | 24 | 2024-04-17 02:24 | 2024-04-25 12:00 | 32 | 2024-07-15 16:48 | 2024-07-26 21:36 |  | Scala programming
Compilers | Advanced Programming | 9 weeks | 6-8 hours/week | 54 | 2024-04-25 12:00 | 2024-05-14 09:36 | 72 | 2024-07-26 21:36 | 2024-08-21 02:24 |  | none
Introduction to Haskell | Advanced Programming | 14 weeks | - | 100 | 2024-05-14 09:36 | 2024-06-18 09:36 | 100 | 2024-08-21 02:24 | 2024-09-25 02:24 |  | -
Learn Prolog Now! | Advanced Programming | 12 weeks | - | 100 | 2024-06-18 09:36 | 2024-07-23 09:36 | 100 | 2024-09-25 02:24 | 2024-10-30 02:24 |  | -
Software Debugging | Advanced Programming | 8 weeks | 6 hours/week | 48 | 2024-07-23 09:36 | 2024-08-09 04:48 | 48 | 2024-10-30 02:24 | 2024-11-15 21:36 |  | Python, object-oriented programming
Software Testing | Advanced Programming | 4 weeks | 6 hours/week | 24 | 2024-08-09 04:48 | 2024-08-17 14:24 | 24 | 2024-11-15 21:36 | 2024-11-24 07:12 |  | Python, programming experience
Final Project | Final Project |  |  | 100 | 2024-08-17 14:24 | 2024-09-21 14:24 | 100 | 2024-11-24 07:12 | 2024-12-29 07:12
Formulas:
Start Date = if(isblank([Actual End Date, row above]),[End Date Estimate Lower Bound, row above],[Actual End Date, row above])
Start Date = if(isblank([Actual End Date, row above]),[End Date Estimate Upper Bound, row above],[Actual End Date, row above])
End Date Estimate Lower Bound = if(isblank([Actual End Date]),[Start Date]+([Total Hours Lower Bound]/(Timeline!$B3/7)),[Actual End Date])
End Date Estimate Upper Bound = if(isblank([Actual End Date]),[Start Date]+([Total Hours Upper Bound]/(Timeline!$B3/7)),[Actual End Date])